**Project Status Report I**

|  |
| --- |
| Date of Report Issue/Prepared: 31/01/2021 |

Report Prepared By: Shishir Das, Sudeep Manandhar

Employer/Organization: Gr14 Development

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health: | Temporary Workspace Management App Development | |
| T15 | |
| Start Date: **Jan 11, 2021** | End Date: **Jan 29, 2021** |
| Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary

|  |
| --- |
| Project Status Summary |
| The project was updated, so that this sprint would not include the profile system as previously planned. However, the service system from sprint 6 was preponed to this sprint. However, the login system was done well, while the registration system couldn’t be completed. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Login system completed | Develop Template (75% Done) |
| Generate staff database and login database | Registration system postponed to sprint 6 |
| Create login page, generate sessions and cookies and link to database | Homepage & Dashboard (Contents need to be added) |
| Service pages design (preponed from sprint 6) have been completed |  |

Upcoming Objectives for Jan 30, 2021 to Feb 12, 2021

|  |  |  |  |
| --- | --- | --- | --- |
| **Planned Activities/Tasks for Next Period** | | | |
| **Activity/Task** | **Assigned To**  **<name/s>** | **Duration**  **<days>** | **Date** |
| Sprint Planning Meeting |  | 1 | 05/02/2021 |
| **Pending from Sprint 5** | | **5** | **05/02/2021** |
| Adding footer to template | Rajesh Bista | 1 | 01/02/2021 |
| Content for home page and dashboard | Sudeep Manandhar,  Kamrun Nahar Liza | 2 | 02/02/2021 |
| Content for service / maintenance pages | Sudeep Manandhar,  Kamrun Nahar Liza | 2 | 04/02/2021 |
| Create premises and resources databases | Suvash Sharma,  Shishir Das | 2 | 02/02/2021 |
| Link Service pages to cart | Suvash Sharma,  Shishir Das | 1 | 03/02/2021 |
| Test login system | Shishir Das | 1 | 05/02/2021 |
| Test request system | Kamrun Nahar Liza | 1 | 05/02/2021 |
|  |  |  |  |
| **Develop login system** | | **5** | **12/02/2021** |
| Create registration page | Rajesh Bista | 1 | 08/02/2021 |
| Generate staff database and login database | Suvash Sharma,  Shishir Das | 1 | 08/02/2021 |
| Create login page, generate sessions and cookies and link to database | Rajesh Bista,  Suvash Sharma,  Shishir Das | 1 | 09/02/2021 |
| Test login system | Sudeep Manandhar,  Kamrun Nahar Liza | 1 | 10/02/2021 |
|  | |  |  |
| **Develop profile system** | |  |  |
| Create individual profile page | Sudeep Manandhar | 1 | 08/02/2021 |
| Create corporate profile page | Kamrun Nahar Liza | 1 | 08/02/2021 |
| Create team profile page for corporate clients | Kamrun Nahar Liza | 1 | 09/02/2021 |
| Link profile to dashboard | Sudeep Manandhar | 1 | 09/02/2021 |
| Test profile system | Rajesh Bista,  Suvash Sharma | 1 | 10/02/2021 |
|  | |  |  |
| **Sprint Review** | | **1** | **11/02/2021** |
| **Sprint Retrospective** | | **1** | **12/02/2021** |

|  |  |  |
| --- | --- | --- |
| **Milestones for Next Period** | | |
| Milestone (Objective) | Assigned To | Delivery Date |
| Login System  Profile System |  |  |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Time management | Communication |  |

|  |  |  |  |
| --- | --- | --- | --- |
| Upcoming Risks | Risk Ranking  (Hi, Med, Low) | Risk Impact  (Hi, Med, Low) | Mitigation Strategy |
|  |  |  |  |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport1”.

For e.g. T36\_ProjectStatusReport1

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, Jan 31, 2021 (11:59 p.m.)**