**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared: 13/02/2021 |

Report Prepared By: Rajesh Bista, Kamrun Nahar Liza

Employer/Organization: Gr14 Development

|  |  |  |
| --- | --- | --- |
| Project Name: | Temporary Workspace Management App Development | |
| Project Team: | T15 | |
| Period Reporting: | Start Date: **Feb 1, 2021** | End Date: **Feb 14, 2021** |
| Overall Project Health: | Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary

|  |
| --- |
| Project Status Summary |
| Approximately 70% of all targets of this sprint were achieved. The contents for home page and dashboard have been completed along with login system and profile system. While templates are almost complete and registration system is well underway, the progress is low with the service request system. The content for service request system is not complete, either. |

|  |  |
| --- | --- |
| **Accomplishments as Planned** | **Planned but not Accomplished** |
| Contents prepared for Homepage & Dashboard | Development of Template is 90% complete. |
| Link Service pages to cart | Contents for service / maintenance pages 20% complete. |
| Login system systems completed | Registration system is 50% complete. |
| Profile system completed | Service request system 30% complete |
| Premises and resources databases completed |  |

Upcoming Objectives for Feb 15, 2021 to Feb 26, 2021

|  |  |  |  |
| --- | --- | --- | --- |
| **Planned Activities/Tasks for Next Period** | | | |
| **Activity/Task** | **Assigned To**  **<name/s>** | **Duration**  **<days>** | **Date** |
| Sprint Planning Meeting |  | 1 | 15/02/2021 |
| **Pending from Previous Sprint** | | **2** | **16/02/2021** |
| Complete template development | Rajesh Bista | 1 | 15/02/2021 |
| Develop content for service pages | Sudeep Manandhar | 2 | 16/02/2021 |
| Add functionalities to link service pages | Rajesh Bista | 1 | 16/02/2021 |
| Complete backend for profile pages | Suvash Sharma | 2 | 16/02/2021 |
| Complete backend for registration pages | Kamrun Nahar Liza | 2 | 16/02/2021 |
| Link profile to service system and database | Shishir Das | 2 | 16/02/2021 |
|  | | | |
| **Develop notification/report system** | | **5** | **2/24/21** |
| Create notification page | Sudeep Manandhar, Rajesh Bista | 1 | 2/17/21 |
| Create notification database | Sudeep Manandhar, Rajesh Bista | 1 | 2/18/21 |
| Link to user dashboards | Sudeep Manandhar | 1 | 2/19/21 |
| Link to service system | Rajesh Bista | 1 | 2/21/21 |
| Test notification/report system | Shishir Das | 2 | 2/24/21 |
|  | | | |
| **Generate Documentation System** | | **5** | **2/19/21** |
| Create documents page with upload and download features | Kamrun Nahar Liza, Shishir Das | 1 | 2/17/21 |
| Develop documents database | Shishir Das, Kamrun Nahar Liza | 1 | 2/18/21 |
| Link documents page to database and dashboard | Shishir Das, Kamrun Nahar Liza | 1 | 2/19/21 |
| Test documentation system | Suvash Sharma | 2 | 2/19/21 |
|  | | | |
| **Develop Checkout System** | | **6** | **2/24/21** |
| Create user confirmation page | Suvash Sharma | 2 | 2/16/21 |
| Create Checkout page | Suvash Sharma | 1 | 2/18/21 |
| Link to notification system | Rajesh Bista, Sudeep Manandhar | 1 | 2/22/21 |
| Link confirmation page to user profile | Suvash Sharma | 1 | 2/22/21 |
| Test checkout system | Kamrun Nahar Liza | 2 | 2/24/21 |
| **Sprint Review** | | **1** | **2/25/21** |
| **Sprint Retrospective** | | **1** | **2/26/21** |

|  |  |  |
| --- | --- | --- |
| **Milestones for Next Period** | | |
| **Milestone (Objective)** | **Assigned To** | **Delivery Date** |
| Notification/Report System  Documentation System  Checkout System |  | **2/24/21**  **2/19/21**  **2/10/21** |

**Managing Issues and Risk**

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Time management (due to multiple course assignments and workloads) | Supportive team environment  Proper division of workload | Due course |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
|  |  |  |  |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport1”.

For e.g. T36\_ProjectStatusReport1

This is a group submission i.e. one per group.

**Due Dates:**

**Sunday, Feb 14, 2021 (11:59 p.m.)**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport2”.

For e.g. T36\_ProjectStatusReport2

This is a group submission ie. one per group.

**Due Dates:**

**Sunday, Feb 14, 2021 (11:59 p.m.)**