**Project Status Report III**

|  |
| --- |
| Date of Report Issue/Prepared: 27/02/2021 |

Report Prepared By: Suvash Sharma, Sudeep Manandhar

Employer/Organization: Gr14 Development

|  |  |  |
| --- | --- | --- |
| Project Name: | Temporary Workspace Management App Development | |
| Project Team: | T15 | |
| Period Reporting: | Start Date: **Feb 15, 2021** | End Date: **Feb 28, 2021** |
| Overall Project Health: | Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary

|  |
| --- |
| Project Status Summary |
| Based on the current project progress status, the overall satisfaction rating is about 65%.  Milestones delivery:  Out of planned three milestones for this sprint, only the ‘checkout system’ had significant progress. However, delivery of ‘notification/report system’ has low progress. The milestone 'documentation system’ has been omitted from the project, as this facility has been incorporated in various sections in and as required.  Overall tasks delivery:  The backend system for registration and profile pages have been completed. The dynamic functionality of several pages and components, such as linking of user profile to services & database, linking to user dashboard & service system, has been completed.  The progress of contents development is almost complete. The remaining tasks for content development and dashboard to database linking are in progress. The frontend and backend tasks planned for ‘notification/reports system’ including testing could not be delivered in this sprint. However, frontend team is working on developing UI template, while backend team is ready to get started once the front end (templates) is delivered.  Due to time pressure, workdays have been expanded to include Saturdays. |

|  |  |
| --- | --- |
| **Accomplishments as Planned** | **Planned but not Accomplished** |
| Project template was completed | Content development for service pages (achieved 95%) |
| Backend for profile pages was completed | Notification System (achieved 20%) |
| Backend for registration pages was completed | Documentation System has been omitted |
| Profile was linked to service system and database | Checkout system (achieved 90%) |
| Functionalities to link service pages were added |  |

Upcoming Objectives for March 01, 2021 to March 12, 2021

|  |  |  |  |
| --- | --- | --- | --- |
| **Planned Activities/Tasks for Next Period** | | | |
| **Activity/Task** | **Assigned To**  **<name/s>** | **Duration**  **<days>** | **Date** |
| Sprint Planning Meeting |  | 1 | 01/03/2021 |
| **Pending from Previous Sprint** | | **2** | **02/03/2021** |
| Develop content for service pages | Sudeep Manandhar | 1 | 01/03/2021 |
| Create notification database | Sudeep Manandhar | 1 | 02/03/2021 |
| Link to user dashboards | Suvash Sharma | 2 | 02/03/2021 |
| Link to service system | Rajesh Bista | 2 | 02/03/2021 |
| Test notification/report system | Shishir Das | 2 | 02/03/2021 |
| Test checkout system | Kamrun Nahar Liza | 2 | 02/03/2021 |
|  | | | |
| **Develop Rating system** | | **6** | **10/03/21** |
| Create feedback and rating page | Rajesh Bista, Shishir Das | 2 | 04/03/21 |
| Create feedback database | Rajesh Bista, Shishir Das | 2 | 06/03/21 |
| Link rating page to home page and dashboard | Rajesh Bista, Shishir Das | 1 | 09/03/21 |
| Test rating system | Kamrun Nahar Liza | 1 | 10/03/21 |
|  | | | |
| **Develop Referral System** | | **5** | **10/03/21** |
| Develop rewards page with loyalty and referral sections | Kamrun Nahar Liza | 3 | 05/03/21 |
| Link referral page with user profile and external email | Kamrun Nahar Liza | 2 | 09/03/21 |
| Test referral system | Shishir Das | 1 | 10/03/21 |
|  | | | |
| **Develop Payment System** | | **8** | **10/03/21** |
| Research the generation of payment system | Sudeep Manandhar, Suvash Sharma | 3 | 06/03/21 |
| Generate a third-party verification system | Sudeep Manandhar, Suvash Sharma | 1 | 07/03/21 |
| Link verification system to checkout page and confirmation page | Suvash Sharma, Sudeep Manandhar | 2 | 09/03/21 |
| Test payment system | Rajesh Bista | 1 | 10/03/21 |
| **Sprint Review** | | **1** | **11/03/21** |
| **Sprint Retrospective** | | **1** | **12/03/21** |

|  |  |  |
| --- | --- | --- |
| **Milestones for Next Period** | | |
| **Milestone (Objective)** | **Assigned To** | **Delivery Date** |
| Notification/Report System  Checkout System  Rating System  Payment System  Referral System |  | **02/03/21**  **02/03/21**  **10/03/21**  **10/03/21**  **10/03/21** |

**Managing Issues and Risk**

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Time management (due to multiple course assignments and workloads)  The midterm and assignments took most of our time, hence less contributions were made to the project. | Supportive team environment  Proper division of workload  The pending works were carried over to next sprint. | Due course  10/03/21 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
|  |  |  |  |

**NOTE: Attach additional sheets if insufficient space available**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport3”.

For eg. T36\_ProjectStatusReport3

This is a group submission ie. one per group.

**Due Dates:**

**Sunday, Feb 28, 2021 (11:59 p.m.)**

**Submission Guidelines:**

Please submit as “T<team number>\_ProjectStatusReport2”.

For eg. T36\_ProjectStatusReport2

This is a group submission ie. one per group.

**Due Dates:**

**Sunday, Feb 28, 2021 (11:59 p.m.)**