## Sheet1
Row# | WBS | Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
1 | 1 | Manually Scheduled | Sprint 5 | 30 hrs | Mon 1/11/21 | Fri 1/29/21
2 | 1.1 | Manually Scheduled | Sprint Planning Meeting | 1 hr | Mon 1/11/21 | Mon 1/11/21 |  | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
3 | 1.2 | Manually Scheduled | Upgrade required hardware/software | 9 hrs | Mon 1/11/21 | Fri 1/15/21 |  | Kamrun Nahar Liza,Suvash Sharma,Shishir Das
4 | 1.3 | Manually Scheduled | Develop template | 9 hrs | Mon 1/11/21 | Fri 1/15/21 |  | Rajesh Bista,Sudeep Manandhar,Kamrun Nahar Liza,Shishir Das,Suvash Sharma
5 | 1.4 | Manually Scheduled | Develop home page and dashboard | 6 hrs | Mon 1/18/21 | Wed 1/20/21
6 | 1.4.1 | Manually Scheduled | Create home page | 4 hrs | Mon 1/18/21 | Tue 1/19/21 | 4 | Suvash Sharma
7 | 1.4.2 | Manually Scheduled | Create dashboard (add admin privilege) | 4 hrs | Mon 1/18/21 | Tue 1/19/21 | 4 | Kamrun Nahar Liza
8 | 1.4.3 | Manually Scheduled | Test home page and dashboard | 2 hrs | Wed 1/20/21 | Wed 1/20/21 | 6,7 | Rajesh Bista,Sudeep Manandhar
9 | 1.5 | Manually Scheduled | Develop service system | 16 hrs | Mon 1/18/21 | Wed 1/27/21
10 | 1.5.1 | Manually Scheduled | Create a dynamic service list in service page | 1 hr | Mon 1/18/21 | Mon 1/18/21 | 4 | Rajesh Bista,Suvash Sharma | Content pending |  | Create a dynamic service list in service page | 1 hr | Content pending
11 | 1.5.2 | Manually Scheduled | Create admin page for service system | 3 hrs | Mon 1/18/21 | Tue 1/19/21 | 4 | Suvash Sharma,Rajesh Bista | Content pending |  | Create admin page for service system | 3 hrs | Content pending
12 | 1.5.3 | Manually Scheduled | Create a service and maintenance request page | 2 hrs | Wed 1/20/21 | Wed 1/20/21 | 4 | Rajesh Bista,Suvash Sharma |  |  | Create premises and resources database | 4 hrs | x
13 | 1.5.4 | Manually Scheduled | Create premises and resources database | 4 hrs | Thu 1/21/21 | Fri 1/22/21 | 4 | Rajesh Bista,Suvash Sharma | x |  | Link service page to cart | 2 hrs | Make everything functional
14 | 1.5.5 | Manually Scheduled | Create a cart | 2 hrs | Mon 1/25/21 | Mon 1/25/21 | 10,11 | Kamrun Nahar Liza,Sudeep Manandhar |  |  | Create registration pages | 3 hrs | Backend not complete
15 | 1.5.6 | Manually Scheduled | Link service page to cart | 2 hrs | Mon 1/25/21 | Mon 1/25/21 | 10,14,11 | Rajesh Bista,Suvash Sharma |  | Make everything functional | Generate staff database and login database | 4 hrs | x
16 | 1.5.7 | Manually Scheduled | Test service system | 4 hrs | Tue 1/26/21 | Wed 1/27/21 | 15SS | Shishir Das |  |  | Create individual profile page | 3 hrs | Backend not complete
17 | 1.6 | Manually Scheduled | Sprint Review | 2 hrs | Thu 1/28/21 | Thu 1/28/21 | 8,16 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma |  |  | Create corporate profile page | 2 hrs | Backend not complete
18 | 1.7 | Manually Scheduled | Sprint Retrospective | 2 hrs | Fri 1/29/21 | Fri 1/29/21 | 17 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma |  |  | Link profile to package and services system | 2 hrs? | x
19 | 2 | Manually Scheduled | Sprint 6 | 20 hrs | Mon 2/1/21 | Fri 2/12/21 |  |  |  |  | Link profile and dashboard to database | 4 hrs | x
20 | 2.1 | Manually Scheduled | Sprint Planning Meeting | 1 hr | Mon 2/1/21 | Mon 2/1/21 | 18 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
21 | 2.2 | Manually Scheduled | Develop login system | 15 hrs | Mon 2/1/21 | Wed 2/10/21
22 | 2.2.1 | Manually Scheduled | Create registration pages | 3 hrs | Mon 2/1/21 | Tue 2/2/21 | 4 | Shishir Das,Rajesh Bista | Backend not complete
23 | 2.2.2 | Manually Scheduled | Generate staff database and login database | 4 hrs | Wed 2/3/21 | Thu 2/4/21 | 4 | Rajesh Bista,Shishir Das | x
24 | 2.2.3 | Manually Scheduled | Create login page, generate sessions and cookies and link to database | 4 hrs | Fri 2/5/21 | Mon 2/8/21 | 4 | Rajesh Bista,Shishir Das |  | Using redux for cookies
25 | 2.2.4 | Manually Scheduled | Test login system | 4 hrs | Tue 2/9/21 | Wed 2/10/21 | 22,23,24 | Suvash Sharma,Kamrun Nahar Liza
26 | 2.3 | Manually Scheduled | Develop profile system | 15 hrs | Mon 1/18/21 | Wed 1/27/21
27 | 2.3.1 | Manually Scheduled | Create individual profile page | 3 hrs | Mon 2/1/21 | Tue 2/2/21 | 25 | Kamrun Nahar Liza,Sudeep Manandhar |  | Backend not complete
28 | 2.3.2 | Manually Scheduled | Create corporate profile page | 2 hrs | Wed 2/3/21 | Wed 2/3/21 | 25 | Kamrun Nahar Liza,Sudeep Manandhar |  | Backend not complete
29 | 2.3.3 | Auto Scheduled | Link profile to package and services system | 2 hrs? | Thu 2/4/21 | Thu 2/4/21 | 16,27,28 | Sudeep Manandhar,Kamrun Nahar Liza |  | x | Purchase history not in plan
30 | 2.3.4 | Manually Scheduled | Link profile and dashboard to database | 4 hrs | Fri 2/5/21 | Mon 2/8/21 | 27,28,8 | Kamrun Nahar Liza,Shishir Das |  | x
31 | 2.3.5 | Manually Scheduled | Test profile system | 4 hrs | Tue 2/9/21 | Wed 2/10/21 | 30 | Rajesh Bista,Suvash Sharma
32 | 2.4 | Manually Scheduled | Sprint Review | 2 hrs | Thu 2/11/21 | Thu 2/11/21 | 31,25 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
33 | 2.5 | Manually Scheduled | Sprint Retrospective | 2 hrs | Fri 2/12/21 | Fri 2/12/21 | 32 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
34 | 3 | Manually Scheduled | Sprint 7 | 20 hrs | Mon 2/15/21 | Fri 2/26/21
35 | 3.1 | Manually Scheduled | Sprint Planning Meeting | 1 hr | Mon 2/15/21 | Mon 2/15/21 | 33 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
36 | 3.2 | Manually Scheduled | Develop notification/report system | 15 hrs | Mon 2/15/21 | Wed 2/24/21
37 | 3.2.1 | Manually Scheduled | Create notification page | 3 hrs | Mon 2/15/21 | Tue 2/16/21 | 5 | Sudeep Manandhar,Rajesh Bista
38 | 3.2.2 | Manually Scheduled | Create notification database | 4 hrs | Wed 2/17/21 | Thu 2/18/21 | 5 | Sudeep Manandhar,Rajesh Bista
39 | 3.2.3 | Manually Scheduled | Link to user dashboards | 4 hrs | Fri 2/19/21 | Mon 2/22/21 | 37,38 | Sudeep Manandhar
40 | 3.2.4 | Manually Scheduled | Link to service system | 4 hrs | Fri 2/19/21 | Mon 2/22/21 | 37,38,9 | Rajesh Bista
41 | 3.2.5 | Manually Scheduled | Test notification/report system | 4 hrs | Tue 2/23/21 | Wed 2/24/21 | 39,40 | Kamrun Nahar Liza
42 | 3.3 | Manually Scheduled | Generate Documentation System | 9 hrs | Mon 2/15/21 | Fri 2/19/21
43 | 3.3.1 | Manually Scheduled | Create documents page with upload and download features | 3 hrs | Mon 2/15/21 | Tue 2/16/21 | 5 | Kamrun Nahar Liza,Shishir Das
44 | 3.3.2 | Manually Scheduled | Develop documents database | 2 hrs | Wed 2/17/21 | Wed 2/17/21 | 5 | Shishir Das,Kamrun Nahar Liza
45 | 3.3.3 | Manually Scheduled | Link documents page to database and dashboard | 2 hrs | Thu 2/18/21 | Thu 2/18/21 | 43,44 | Shishir Das,Kamrun Nahar Liza
46 | 3.3.4 | Manually Scheduled | Test documentation system | 2 hrs | Fri 2/19/21 | Fri 2/19/21 | 45 | Suvash Sharma
47 | 3.4 | Manually Scheduled | Develop checkout system | 15 hrs | Mon 2/1/21 | Wed 2/10/21
48 | 3.4.1 | Manually Scheduled | Create user confirmation page | 3 hrs | Mon 2/15/21 | Tue 2/16/21 | 14 | Suvash Sharma
49 | 3.4.2 | Manually Scheduled | Create Checkout page | 4 hrs | Wed 2/17/21 | Thu 2/18/21 | 48 | Suvash Sharma
50 | 3.4.3 | Manually Scheduled | Link to notification system | 2 hrs | Fri 2/19/21 | Fri 2/19/21 | 36,48,49 | Rajesh Bista,Sudeep Manandhar
51 | 3.4.4 | Manually Scheduled | Link confirmation page to user profile | 2 hrs | Sat 2/20/21 | Sat 2/20/21 | 48,26 | Suvash Sharma
52 | 3.4.5 | Manually Scheduled | Test checkout system | 4 hrs | Tue 2/23/21 | Wed 2/24/21 | 51 | Sudeep Manandhar
53 | 3.5 | Manually Scheduled | Sprint Review | 2 hrs | Thu 2/25/21 | Thu 2/25/21 | 52,41,46 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
54 | 3.6 | Manually Scheduled | Sprint Retrospective | 2 hrs | Fri 2/26/21 | Fri 2/26/21 | 53 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
55 | 4 | Manually Scheduled | Sprint 8 | 20 hrs | Mon 3/1/21 | Fri 3/12/21
56 | 4.1 | Manually Scheduled | Sprint Planning Meeting | 1 hr | Mon 3/1/21 | Mon 3/1/21 | 54 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
57 | 4.2 | Manually Scheduled | Develop rating system | 9 hrs | Mon 3/1/21 | Fri 3/5/21
58 | 4.2.1 | Manually Scheduled | Create feedback and rating page | 3 hrs | Mon 3/1/21 | Tue 3/2/21 | 5 | Rajesh Bista,Shishir Das
59 | 4.2.2 | Manually Scheduled | Create feedback database | 2 hrs | Wed 3/3/21 | Wed 3/3/21 |  | Rajesh Bista,Shishir Das
60 | 4.2.3 | Manually Scheduled | Link rating page to home page and dashboard | 2 hrs | Thu 3/4/21 | Thu 3/4/21 | 58,5 | Rajesh Bista,Shishir Das
61 | 4.2.4 | Manually Scheduled | Test rating system | 2 hrs | Fri 3/5/21 | Fri 3/5/21 | 60 | Kamrun Nahar Liza
62 | 4.3 | Manually Scheduled | Develop Payment System | 15 hrs | Mon 3/1/21 | Wed 3/10/21
63 | 4.3.1 | Auto Scheduled | Research the generation of payment system | 3 hrs | Mon 3/1/21 | Tue 3/2/21 |  | Sudeep Manandhar,Suvash Sharma
64 | 4.3.2 | Auto Scheduled | Generate a third party verification system | 4 hrs | Wed 3/3/21 | Thu 3/4/21 | 47,63 | Sudeep Manandhar,Suvash Sharma
65 | 4.3.3 | Auto Scheduled | Link verification system to checkout page and confirmation page | 4 hrs | Fri 3/5/21 | Mon 3/8/21 | 47,64 | Suvash Sharma,Sudeep Manandhar
66 | 4.3.4 | Auto Scheduled | Test payment system | 4 hrs | Tue 3/9/21 | Wed 3/10/21 | 65 | Kamrun Nahar Liza
67 | 4.4 | Manually Scheduled | Develop referral system | 8 hrs | Fri 3/5/21 | Wed 3/10/21
68 | 4.4.1 | Manually Scheduled | Develop rewards page with loyalty and referral sections | 4 hrs | Fri 3/5/21 | Mon 3/8/21 | 5 | Shishir Das,Rajesh Bista
69 | 4.4.2 | Manually Scheduled | Link referral page with user profile and external email | 2 hrs | Tue 3/9/21 | Tue 3/9/21 | 26,68 | Rajesh Bista,Shishir Das
70 | 4.4.3 | Manually Scheduled | Test referral system | 2 hrs | Wed 3/10/21 | Wed 3/10/21 | 69 | Sudeep Manandhar
71 | 4.5 | Manually Scheduled | Sprint Review | 2 hrs | Thu 2/11/21 | Thu 2/11/21 | 61,70,66 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
72 | 4.6 | Manually Scheduled | Sprint Retrospective | 2 hrs | Fri 2/12/21 | Fri 2/12/21 | 71 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
73 | 5 | Manually Scheduled | Sprint 9 | 20 hrs | Mon 3/15/21 | Fri 3/26/21
74 | 5.1 | Manually Scheduled | Sprint Planning Meeting | 1 hr | Mon 3/15/21 | Mon 3/15/21 | 72 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
75 | 5.2 | Manually Scheduled | Function Testing | 5 hrs | Mon 3/15/21 | Wed 3/17/21 | 1,19,34,55 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
76 | 5.3 | Manually Scheduled | System Testing | 8 hrs | Thu 3/18/21 | Tue 3/23/21 | 75 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
77 | 5.4 | Manually Scheduled | User Acceptance Testing | 10 hrs | Wed 3/24/21 | Tue 3/30/21 | 76 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
78 | 5.5 | Manually Scheduled | Sprint Review | 2 hrs | Wed 3/31/21 | Wed 3/31/21 | 77 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
79 | 5.6 | Manually Scheduled | Sprint Retrospective | 2 hrs | Thu 4/1/21 | Thu 4/1/21 | 78 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma
80 | 6 | Manually Scheduled | Project Completion Meeting | 2 hrs | Fri 4/2/21 | Fri 4/2/21 | 73 | Kamrun Nahar Liza,Rajesh Bista,Shishir Das,Sudeep Manandhar,Suvash Sharma