## Slide 1: Temporary Workspace Management App Project
Kamrun Nahar Liza
Rajesh Bista
Shishir Das
Sudeep Manandhar
Suvash Sharma

## Slide 2: Project Introduction

## Slide 3: PROJECT DETAILS
  Temporary Workspace Management App Project
Project
  14 September 2020 – 02 April 2021
Duration
  To help temporary workspace management company (TWM) automatize their business processes and provide a platform for their clients to get connected with them conveniently
Objective
  Clients of TWM company will have a secured, optimized and user-friendly web application by 2021 to find the office space that suits the need of their business
Corporate Goal

## Slide 4: PROJECT OUTCOMES
Web-based Application
  Client management
  Automation of services / info
  Client-friendly interface

## Slide 5: PROJECT TEAM
Kamrun Nahar Liza
Rajesh Bista
Shishir Das
Suvash Sharma
Sudeep Manandhar
Product Owner
Middleware
UI/UX
Frontend Designer
Quality Analyst
Backend Developer
Scrum Master
Frontend Designer

## Slide 6: PROJECT TEAM
Kamrun Nahar Liza
Rajesh Bista
Shishir Das
Sudeep Manandhar
Suvash Sharma

## Slide 7: Status Update: Sprint 5

## Slide 8: ACCOMPLISHMENTS
Login system completed
Staff database and login database completed
Sessions and cookies managed
Packages and Services pages design completed
  Preponed from sprint 6
Template (75% done)
  Continuing without any interference to the planned sprints
Registration system postponed
Contents postponed to Sprint 6
  Homepage
  Dashboard
  Packages & Services

## Slide 9: UPDATED PLAN
Milestones | Sprint
Develop home page and dashboard | 5
Develop service system | 5
Develop login system | 6
Develop profile system | 6
Develop notification/report system | 7
Generate Documentation System | 7
Develop checkout and payment system | 
Checkout | 7
Payment | 8
Develop rating system | 8
Develop reference system | 8

## Slide 10: UPDATES
Database
  MongoDB: for database
  Firebase: for authentication
  Previous plan: MySQL

## Slide 11: CHALLENGES
Time Management
  Demand on our time for all the courseworks
Communication Issues
  Network problems
  Lack of physical contact