## User Stories
Product Backlog
SN | As a… | I want to be able to… | so that… | Priority | Sprint | Status
1 | As a corporate client, I should be able to… | register and create company profile | so that I can perform all the operations needed as a corporate entity on behalf of the company | M | 1,2 | TBS | MoSCoW model
2 |  | login to the system | so that I can securely operate all the tasks for our employees | M | 1 | TBS | M - Must Have
3 |  | create teams | so that I can define and address the specific needs as per team | M | 1 | TBS | S - Should Have
5 |  | add team members into appropriate teams | to form one or more well-defiend team as per the company requirement | S | 1 | TBS | C - Could Have
6 |  | remove team members from teams | so that I can manage and update the team if there is any change in team member | S | 1 | TBS | W - Won't Have
7 |  | move members from one team to another | so that when an employee needs to switch team | C | 1 | TBS | TBS - To Be Started
8 |  | make payments through third parties | so that the paid services can be provided to the employees | M | 3 | TBS
9 |  | request for maintenance | so that the company can keep track of fees and can pay directly from the company | M | 2 | TBS
10 | As an individual client, I should be able to… | Register, create profile and login to the system | So that I can access the services offered by TVM company | M | 1,2 | TBS
11 |  | View the list of all available services | So that I can select the services of my need | M | 2 | TBS
12 |  | Book a tour or arrange a meeting | So that I can visit the premises to make sure the information provided online are accurate and match my requirement. | S | 2 | TBS
13 |  | Upload and download documents | So that I can receive and supply the required information electronically at my convenience | S | 4 | TBS
14 |  | Pay online | So that I can securely make the payments for the payable transactions I made. | M | 3 | TBS
15 |  | Initiate repair/maintenance request | So that I can promptly reach out and receive the repair services as and when needed. | M | 2 | TBS
16 |  | Get notifications | So that I can get regular updates about services or transactions | M | 3 | TBS
17 |  | Refer clients and view my loyalty rewards | So that I can receive my loyalty rewards and referral bonus. | C | 4 | TBS
18 |  | update my profile | so that I can provide my up-to-date information. |  | 2 | TBS
19 |  | Rate the services | So that I can provide the feedback on the services. | S | 4 | TBS
20 | As an App Admin, I should be able to… | login to the system with elevated permissions | so I can change the settings and manage the app | M | 1 | TBS
21 |  | approve users into the system | so that the users can login into the system | M | 1 | TBS
22 |  | update the services provided | so that the company can launch new packages and customize them | M | 2 | TBS
23 |  | backup database | so that I can keep the database safe | M | 1 | TBS
24 |  | apply user permsissions | so that different roles can be assigned to different users | M | 5 | TBS
25 |  | get monthly reports | so that I can view maintainance records and support the company in making business decisions | M | 3 | TBS
26 | As a staff, I should be able to… | login to the system | I can perform my duties in my job | M | 1 | TBS
27 |  | register clients | so they can begin receiving services from TWM | M | 1 | TBS
28 |  | address the requests sent by the clients | so they can receive the desired services | M | 2 | TBS

## Sprint1
Sprint Backlog: Sprint 1
SN | As a… | I want to be able to… | so that… | Priority | Status
1 | As a corporate client, I should be able to… | register and create company profile | so that I can perform all the operations needed as a corporate entity on behalf of the company | M | TBS | MoSCoW model
2 |  | login to the system | so that I can securely operate all the tasks for our employees | M | TBS | M - Must Have
3 |  | create teams | so that I can define and address the specific needs as per team | M | TBS | S - Should Have
5 |  | add team members into appropriate teams | to form one or more well-defiend team as per the company requirement | S | TBS | C - Could Have
6 |  | remove team members from teams | so that I can manage and update the team if there is any change in team member | S | TBS | W - Won't Have
7 |  | move members from one team to another | so that when an employee needs to switch team | C | TBS | TBS - To Be Started
10 | As an individual client, I should be able to… | Register, create profile and login to the system | So that I can access the services offered by TVM company | M | TBS
20 | As an App Admin, I should be able to… | login to the system with elevated permissions | so I can change the settings and manage the app | M | TBS
21 |  | approve users into the system | so that the users can login into the system | M | TBS
23 |  | backup database | so that I can keep the database safe | M | TBS
26 | As a staff, I should be able to… | login to the system | I can perform my duties in my job | M | TBS
27 |  | register clients | so they can begin receiving services from TWM | M | TBS

## Sprint2
Sprint Backlog: Sprint 2
SN | As a… | I want to be able to… | so that… | Priority | Sprint | Status
1 | As a corporate client, I should be able to… | register and create company profile | so that I can perform all the operations needed as a corporate entity on behalf of the company | M | 1,2 | TBS | MoSCoW model
9 |  | request for maintenance | so that the company can keep track of fees and can pay directly from the company | M | 2 | TBS | M - Must Have
10 | As an individual client, I should be able to… | Register, create profile and login to the system | So that I can access the services offered by TVM company | M | 1,2 | TBS | S - Should Have
11 |  | View the list of all available services | So that I can select the services of my need | M | 2 | TBS | C - Could Have
12 |  | Book a tour or arrange a meeting | So that I can visit the premises to make sure the information provided online are accurate and match my requirement. | S | 2 | TBS | W - Won't Have
15 |  | Initiate repair/maintenance request | So that I can promptly reach out and receive the repair services as and when needed. | M | 2 | TBS | TBS - To Be Started
18 |  | update my profile | so that I can provide my up-to-date information. |  | 2 | TBS
22 | As an App Admin, I should be able to… | update the services provided | so that the company can launch new packages and customize them | M | 2 | TBS
28 | As a staff, I should be able to… | address the requests sent by the clients | so they can receive the desired services | M | 2 | TBS

## Sprint3
Sprint Backlog: Sprint 3
SN | As a… | I want to be able to… | so that… | Priority | Sprint | Status
8 | As a corporate client, I should be able to… | make payments through third parties | so that the paid services can be provided to the employees | M | 3 | TBS | MoSCoW model
14 | As an individual client, I should be able to… | Pay online | So that I can securely make the payments for the payable transactions I made. | M | 3 | TBS | M - Must Have
16 |  | Get notifications | So that I can get regular updates about services or transactions | M | 3 | TBS | S - Should Have
25 | As an App Admin, I should be able to… | get monthly reports | so that I can view maintainance records and support the company in making business decisions | M | 3 | TBS | C - Could Have
W - Won't Have
TBS - To Be Started

## Sprint4
Sprint Backlog: Sprint 4
SN | As a… | I want to be able to… | so that… | Priority | Sprint | Status
13 | As an individual client, I should be able to… | Upload and download documents | So that I can receive and supply the required information electronically at my convenience | S | 4 | TBS | MoSCoW model
17 |  | Refer clients and view my loyalty rewards | So that I can receive my loyalty rewards and referral bonus. | C | 4 | TBS | M - Must Have
19 |  | Rate the services | So that I can provide the feedback on the services. | S | 4 | TBS | S - Should Have
C - Could Have
W - Won't Have
TBS - To Be Started